## VDI-QOC-6001
Vendor Document Index
Vendor Document Index should be submitted in quotation stage and finalized in kick-off meeting.
CTCI P.O. No. | 20P4300A03-M0023
P.O. Title | Requisition For Pipeline Closure (AG) of CPC Back-up (PPNG Pipeline)
CTCI Requisition No. | 20P4300A03-M99A.51A Rev.1
RE Name: | Rod Wu
1. CTCI Doc. No. |  |  |  |  | 7. Document Status : shall be issued to client for review please key in " O ", for CTCI review only please key in " I "
2. Vendor Document No. |  |  |  |  | 8. Document Issue Type R:For Review, I:For Information
3. Client document No. |  |  |  |  | 9. Vendor plan first issue to CTCI date (yyyy/mm/dd)
4. Description of the document |  |  |  |  | 10. Planned CTCI Approve Date(yyyy/mm/dd)
5. The Main Equipment Tag No. |  |  |  |  | 11. Planned Issue To Client Date (yyyy/mm/dd)
6. Doc Category :
P(3D) : Required vendor documents for 60% 3D Modeling and Model review.
P : Primary required vendor documents to support EPC contractor's engineering efforts.
S : Secondry required vendor documents to support EPC contractor's engineering efforts.
F : Required vendor documents for finish fabrication.
M : Manufacture data / record book.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
CTCI Doc. No. (Required field) | Vendor Doc. No. (Required field) | Client Doc No | Description (Required field) | Main Equipment Tag No. (Required field) | Doc Category (Required field) | Document Status (Required field) | Document Issue Type (Required field) | Vendor Planned 1st Issue Date (Required field) | Planned CTCI Approve Date (Required field) | Planned Issue To Client Date | NOTE
20P4300A03-M0023-001 | 20P4300A03-M0023-TCTI-001 | A2-2-PEM02-V0023A03-001 | Vendor Document Index | QOC-6001 | S | I | R | 01/17/2023 | 02/07/2023
20P4300A03-M0023-002 | 20P4300A03-M0023-TCTI-002 | A2-2-PEM02-V0023A03-002 | Fabrication/Production Schedule Plan (Include Design, Materials Purchasing, Fabrication, Testing and Inspections and Packing...) | QOC-6001 | S | I | R | 2W after receipt of code 1 Approved drawing.
20P4300A03-M0023-003 | 20P4300A03-M0023-TCTI-003 | A2-2-PEM02-V0023A03-003 | Tables Of Contents For R01(MDB) | QOC-6001 | M | I | R | 02/02/2023 | 02/16/2023
20P4300A03-M0023-004 | 20P4300A03-M0023-TCTI-004 | A2-2-PEM02-V0023A03-004 | Organization Chart | QOC-6001 | S | I | I | 02/02/2023 | 02/16/2023
20P4300A03-M0023-005 | 20P4300A03-M0023-TCTI-005 | A2-2-PEM02-V0023A03-005 | Maunfacturer Registration Certificate | QOC-6001 | M | I | I | 02/02/2023 | 02/16/2023
20P4300A03-M0023-006 | 20P4300A03-M0023-TCTI-006 | A2-2-PEM02-V0023A03-006 | TDW India Company Registration Certificate | QOC-6001 | M | I | I | 02/02/2023 | 02/16/2023
20P4300A03-M0023-007 | 20P4300A03-M0023-TCTI-007 | A2-2-PEM02-V0023A03-007 | GA Drawing along with Design Calculation | QOC-6001 | 3D | I | R | 02/02/2023 | 02/16/2023 |  | Drawings in PDF version shall be provided
20P4300A03-M0023-008 | 20P4300A03-M0023-TCTI-008 | A2-2-PEM02-V0023A03-008 | Nameplate Drawings (Including Method of Identification of Spool Piece) | QOC-6001 | S | I | R | 02/02/2023 | 02/16/2023
20P4300A03-M0023-009 | 20P4300A03-M0023-TCTI-009 | A2-2-PEM02-V0023A03-009 | Inspection Test Plan for Closure | QOC-6001 | P | I | I | 02/02/2023 | 02/16/2023
20P4300A03-M0023-010 | 20P4300A03-M0023-TCTI-010 | A2-2-PEM02-V0023A03-010 | Inspection Test Plan for Pig SIG | QOC-6001 | P | I | I | 02/02/2023 | 02/16/2023
20P4300A03-M0023-011 | 20P4300A03-M0023-TCTI-011 | A2-2-PEM02-V0023A03-011 | Vendor Catalogues | QOC-6001 | F | I | I | 02/02/2023 | 02/16/2023
20P4300A03-M0023-012 | 20P4300A03-M0023-TCTI-012 | A2-2-PEM02-V0023A03-012 | ISO/ CE Certificate (ISO 9001/ API Spec Q1) & HSE Assurance (ISO 14001 or EQ.) | QOC-6001 | S | I | I | 02/02/2023 | 02/16/2023
20P4300A03-M0023-013 | 20P4300A03-M0023-TCTI-013 | A2-2-PEM02-V0023A03-013 | Experience List | QOC-6001 | NA | I | I | 02/02/2023 | 02/16/2023
20P4300A03-M0023-014 | 20P4300A03-M0023-TCTI-014 | A2-2-PEM02-V0023A03-014 | Manual Of Installation Operating & Maintenance (IOM) | QOC-6001 | F | I | I | 02/02/2023 | 02/16/2023
20P4300A03-M0023-015 | 20P4300A03-M0023-TCTI-015 | A2-2-PEM02-V0023A03-015 | Hydrostatic or Pneumatic Test Procedures | QOC-6001 | M | I | R | 02/02/2023 | 02/16/2023
20P4300A03-M0023-016 | 20P4300A03-M0023-TCTI-016 | A2-2-PEM02-V0023A03-016 | Non-Destructive Test Procedures | QOC-6001 | S | I | R | 02/02/2023 | 02/16/2023
20P4300A03-M0023-017 | 20P4300A03-M0023-TCTI-017 | A2-2-PEM02-V0023A03-017 | Weld Procedure Specifications & PQR | QOC-6001 | S | I | I | 02/02/2023 | 02/16/2023
20P4300A03-M0023-018 | 20P4300A03-M0023-TCTI-018 | A2-2-PEM02-V0023A03-018 | Packing Procedures for Shipping | QOC-6001 | S | I | I | 02/02/2023 | 02/16/2023
20P4300A03-M0023-019 | 20P4300A03-M0023-TCTI-019 | A2-2-PEM02-V0023A03-019 | PMI Report for PIG-SIG® V | QOC-6001 | S | I | R | 2 Weeks after Inspection of the PIG-SIG® V
20P4300A03-M0023-020 | 20P4300A03-M0023-TCTI-020 | A2-2-PEM02-V0023A03-020 | Quality Dossier Report | QOC-6001 | F | I | R | 18 Week from drawing Approval
20P4300A03-M0023-021 | 20P4300A03-M0023-TCTI-020 | A2-2-PEM02-V0023A03-021 | Inspection And Test Reports (All Other Test Reports) | QOC-6001 | F | I | I | 18 Week from drawing Approval |  |  | Part of Quality Dossier
20P4300A03-M0023-022 | 20P4300A03-M0023-TCTI-020 | A2-2-PEM02-V0023A03-022 | Material Test Certificate (MTC) | QOC-6001 | F | I | I | 18 Week from drawing Approval
20P4300A03-M0023-023 | 20P4300A03-M0023-TCTI-020 | A2-2-PEM02-V0023A03-023 | Quality documents with MTR (Material Test Report ) and COC | QOC-6001 | F | I | I | 18 Week from drawing Approval
20P4300A03-M0023-024 | 20P4300A03-M0023-TCTI-020 | A2-2-PEM02-V0023A03-024 | Painting Inspection Report | QOC-6001 | F | I | R | 18 Week from drawing Approval
20P4300A03-M0023-025 | 20P4300A03-M0023-TCTI-020 | A2-2-PEM02-V0023A03-025 | Hydrotest Report for Closure | QOC-6001 | F | I | R | 18 Week from drawing Approval
20P4300A03-M0023-026 | 20P4300A03-M0023-TCTI-020 | A2-2-PEM02-V0023A03-026 | Hydrotest Report for Pig-SIG | QOC-6001 | F | I | R | 18 Week from drawing Approval
20P4300A03-M0023-027 | 20P4300A03-M0023-TCTI-020 | A2-2-PEM02-V0023A03-027 | Non-Destructive Test Reports | QOC-6001 | F | I | R | 18 Week from drawing Approval |  |  | Report for Dye penetration inspection on the welding shall be provided and it will be a part of Qualiy dossier only
20P4300A03-M0023-028 | 20P4300A03-M0023-TCTI-021 | A2-2-PEM02-V0023A03-028 | Calibration Certificate | QOC-6001 | F | I | I | 18 Week from drawing Approval
20P4300A03-M0023-029 | 20P4300A03-M0023-TCTI-022 | A2-2-PEM02-V0023A03-029 | Packing List (Including Inspection Release Certificate) (a) Wooden Case Package or Fumigation Certificate, or (b) Non-Wooden Case Packing Certificate, or (c) Non-Conifer Wooden Case Certificate | QOC-6001 | M | I | R | after 18 weeks from approved drawing |  |  | Packing list along with packing photograph shall be provided
20P4300A03-M0023-030 | 20P4300A03-M0023-TCTI-023 | A2-2-PEM02-V0023A03-030 | Origin Certificate | QOC-6001 | M | I | I | after 18 weeks from approved drawing |  |  | Certificate of Origin signed and stamped by federation of Gujarat Industries shall be provided
20P4300A03-M0023-031 | 20P4300A03-M0023-TCTI-024 | A2-2-PEM02-V0023A03-031 | EN 10204-3.2 Testing Report (Done in TUV Scope for Raw Materials-Closure) | QOC-6001 | F | I | R | 18 Week from drawing Approval |  |  | 3.2 Certification shall be mentioned on the MTC of raw forgings of Closures dully signed by TUV
20P4300A03-M0023-032 | 20P4300A03-M0023-TCTI-025 | A2-2-PEM02-V0023A03-032 | EN 10204-3.2 Testing Report (Done in TUV Scope for Raw Materials-Pig SIG) | QOC-6001 | F | I | R | 18 Week from drawing Approval |  |  | 3.2 Certification shall be mentioned on the MTC of Flange of PIG-SIG®V Flange dully signed by TUV
20P4300A03-M0023-033 | 20P4300A03-M0023-TCTI-026 | A2-2-PEM02-V0023A03-033 | Final Vendor Documents/Data Book | QOC-6001 | M | I | I | 21 week after drawing approval
20P4300A03-M0023-034 | 20P4300A03-M0023-TCTI-026 | A2-2-PEM02-V0023A03-034 | Manufacturer’s Data/Record Book, MDRM) | QOC-6001 | M | I | I | 21 week after drawing approval |  |  | Part of Final Vendor Document.
20P4300A03-M0023-035 | 20P4300A03-M0023-TCTI-027 | A2-2-PEM02-V0023A03-035 | Packing Drawing, including Dimensions, Weight and Drawing | QOC-6001 | M | I | I | 1 week after receipt of dispatch clearance from customer
Note on F22: P(3D)： Required vendor documents for 60% 3D Modeling and Model review. P：Primary required vendor documents to support EPC contractor's engineering efforts. S：Secondry required vendor documents to support EPC contractor's engineering efforts. F： Required vendor documents for finish fabrication. M：Manufacture data book.
Note on G22: O：For Client Review (Official) I ：For CTCI Review (Internal)
Note on H22: R：For Review I：For Reference
Note on J22: Vendor Planned Issue Date + 14 calendar days
Note on K22: Vendor Planned Issue Date + 7 calendar days