## VDI
Vendor Document Index
Vendor Document Index should be submitted in quotation stage and finalized in kick-off meeting.
CTCI P.O. No. | 20P4300A03-M0021
P.O. Title | Requisition for LV Distribution Panel (MCC) for CPC Back-up (PP NG Pipeline)
CTCI Requisition No. | 20P4300A03-NC4A.01A
RE Name: | Po-Yen,Chen
1. CTCI Doc. No. |  |  |  |  | 7. Document Status : shall be issued to client for review please key in " O ", for CTCI review only please key in " I "
2. Vendor Document No. |  |  |  |  | 8. Document Issue Type R:For Review, I:For Information
3. Client document No. |  |  |  |  | 9. Vendor plan first issue to CTCI date (yyyy/mm/dd)
4. Description of the document |  |  |  |  | 10. Planned CTCI Approve Date(yyyy/mm/dd)
5. The Main Equipment Tag No. |  |  |  |  | 11. Planned Issue To Client Date (yyyy/mm/dd)
6. Doc Category :
P(3D) : Required vendor documents for 60% 3D Modeling and Model review.
P : Primary required vendor documents to support EPC contractor's engineering efforts.
S : Secondry required vendor documents to support EPC contractor's engineering efforts.
F : Required vendor documents for finish fabrication.
M : Manufacture data / record book.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
CTCI Doc. No. (Required field) | Vendor Doc. No. (Required field) | Client Doc No | Description (Required field) | Main Equipment Tag No. (Required field) | Doc Category (Required field) | Document Status (Required field) | Document Issue Type (Required field) | Vendor Planned 1st Issue Date (Required field) | Planned CTCI Approve Date (Required field) | Planned Issue To Client Date
20P4300A03-M0021-001 | 20P4300A03-M0021-001 | A2-2-ELM02-V0021A03-001 | Vendor Document Index (VDI) for LV MCC for CPC Back-up (PP NG Pipeline) | 480V PR MOV STARTER | P | O | R | 2022-12-30 | 2023-01-13 | 2023-01-06 | LV MCC 的供應商文檔索引 (VDI) | 設計
20P4300A03-M0021-002 | 20P4300A03-M0021-002 | A2-2-ELM02-V0021A03-002 | Manufacturing Schedule for LV MCC for CPC Back-up (PP NG Pipeline) | 480V PR MOV STARTER | F | O | R | 2022-12-30 | 2023-01-13 | 2023-01-06 | LV MCC 製造計劃 | 生管
20P4300A03-M0021-003 | 20P4300A03-M0021-003 | A2-2-ELM02-V0021A03-003 | General Arrangement Drawing (Including Foundation Design Base and Anchor Details) for LV MCC for CPC Back-up (PP NG Pipeline) | 480V PR MOV STARTER | P | O | R | 2023-02-17 | 2023-03-03 | 2023-02-24 | LV MCC 總佈置圖（包括基礎設計基礎和錨固細節） | 設計
20P4300A03-M0021-004 | 20P4300A03-M0021-004 | A2-2-ELM02-V0021A03-004 | Specification and Catalogs for LV MCC for CPC Back-up (PP NG Pipeline) | 480V PR MOV STARTER | P | O | R | 2023-02-17 | 2023-03-03 | 2023-02-24 | 低壓 MCC 的規格和目錄 | 設計
20P4300A03-M0021-005 | 20P4300A03-M0021-005 | A2-2-ELM02-V0021A03-005 | Test and Inspection Procedure (Including Factory Acceptance Test and Site Acceptance Test) for LV MCC for CPC Back-up (PP NG Pipeline) | 480V PR MOV STARTER | P | O | R | 2023-03-28 | 2023-04-11 | 2023-04-04 | LV MCC 測試和檢驗程序（包括工廠驗收測試和現場驗收測試） | 品保
20P4300A03-M0021-006 | 20P4300A03-M0021-006 | A2-2-ELM02-V0021A03-006 | Certificate of Conformity for LV MCC for CPC Back-up (PP NG Pipeline) | 480V PR MOV STARTER | S | O | R | 2023-03-28 | 2023-04-11 | 2023-04-04 | LV MCC 合格證書 | 品保
20P4300A03-M0021-007 | 20P4300A03-M0021-007 | A2-2-ELM02-V0021A03-007 | Factory Acceptance Test (FAT) Report/Record Sheet for LV MCC for CPC Back-up (PP NG Pipeline) | 480V PR MOV STARTER | S | O | R | 2023-07-31 | 2023-08-14 | 2023-08-07 | LV MCC 工廠驗收測試 (FAT) 報告/記錄表 | 品保
20P4300A03-M0021-008 | 20P4300A03-M0021-008 | A2-2-ELM02-V0021A03-008 | Site Acceptance Test Report/Record Sheet for LV MCC for CPC Back-up (PP NG Pipeline) | 480V PR MOV STARTER | S | O | R | 2023-10-30 | 2023-11-13 | 2023-11-06 | LV MCC現場驗收測試報告/記錄表 | 品保
20P4300A03-M0021-009 | 20P4300A03-M0021-009 | A2-2-ELM02-V0021A03-009 | Monthly Status Report for MCC for CPC Back-up (PP NG Pipeline) | 480V PR MOV STARTER | F | O | R | 2023-01-25 | 2023-02-08 | 2023-02-01 | MCC 月度狀態報告 | 生管
20P4300A03-M0021-010 | 20P4300A03-M0021-010 | A2-2-ELM02-V0021A03-010 | Packing List for LV MCC for CPC Back-up (PP NG Pipeline) | 480V PR MOV STARTER | F | O | R | 2023-02-15 | 2023-03-01 | 2023-02-22 | LV MCC裝箱單 | 生管
20P4300A03-M0021-011 | 20P4300A03-M0021-011 | A2-2-ELM02-V0021A03-011 | Packing, Knockdown and Transportation Procedure for CPC Back-up (PP NG Pipeline) | 480V PR MOV STARTER | F | O | R | 2023-02-15 | 2023-03-01 | 2023-02-22 | 包裝、拆卸和運輸程序 | 生管
20P4300A03-M0021-012 | 20P4300A03-M0021-012 | A2-2-ELM02-V0021A03-012 | Inspection Test Plan (ITP) for LV MCC for CPC Back-up (PP NG Pipeline) | 480V PR MOV STARTER | P | O | R | 2023-03-28 | 2023-04-11 | 2023-04-04 | LV MCC 檢驗測試計劃 (ITP) | 品保
20P4300A03-M0021-013 | 20P4300A03-M0021-013 | A2-2-ELM02-V0021A03-013 | Single Line Diagram for LV MCC for CPC Back-up (PP NG Pipeline) | 480V PR MOV STARTER | P | O | R | 2023-02-17 | 2023-03-03 | 2023-02-24 | LV MCC 的單線圖 | 設計
20P4300A03-M0021-014 | 20P4300A03-M0021-014 | A2-2-ELM02-V0021A03-014 | Sub-Vendor List for LV MCC for CPC Back-up (PP NG Pipeline) | 480V PR MOV STARTER | S | O | R | 2023-02-15 | 2023-03-01 | 2023-02-22 | LV MCC 子供應商列表 | 設計
20P4300A03-M0021-015 | 20P4300A03-M0021-015 | A2-2-ELM02-V0021A03-015 | Manufacturer's Data/Record Book (MDRB) Index for LV MCC for CPC Back-up (PP NG Pipeline) | 480V PR MOV STARTER | M | O | R | 2023-02-15 | 2023-03-01 | 2023-02-22 | LV MCC 的製造商數據/記錄簿 (MDRB) 索引 | 生管
20P4300A03-M0021-016 | 20P4300A03-M0021-016 | A2-2-ELM02-V0021A03-016 | Manufacturer's Data/Record Book (MDRB) for LV MCC for CPC Back-up (PP NG Pipeline) | 480V PR MOV STARTER | M | O | R | 2023-08-31 | 2023-09-14 | 2023-09-07 | LV MCC 的製造商數據/記錄簿 (MDRB) | 生管
20P4300A03-M0021-017 | 20P4300A03-M0021-017 | A2-2-ELM02-V0021A03-017 | Schematic and Connection Diagram for LV MCC for CPC Back-up (PP NG Pipeline) | 480V PR MOV STARTER | S | O | R | 2023-02-17 | 2023-03-03 | 2023-02-24 | 低壓 MCC 的原理圖和連接圖 | 設計
20P4300A03-M0021-018 | 20P4300A03-M0021-018 | A2-2-ELM02-V0021A03-018 | Mandatory Spare Parts List for LV MCC for CPC Back-up (PP NG Pipeline) | 480V PR MOV STARTER | F | O | R | 2023-02-15 | 2023-03-01 | 2023-02-22 | LV MCC 強製備件清單 | 設計
20P4300A03-M0021-019 | 20P4300A03-M0021-019 | A2-2-ELM02-V0021A03-019 | Erection, Pre-Commissioning, Commissioning, and Start-up Spare Parts List for LV MCC for CPC Back-up (PP NG Pipeline) | 480V PR MOV STARTER | F | O | R | 2023-02-15 | 2023-03-01 | 2023-02-22 | LV MCC 的安裝、預調試、調試和啟動備件清單 | 設計
20P4300A03-M0021-020 | 20P4300A03-M0021-020 | A2-2-ELM02-V0021A03-020 | Consumable Spare Parts List for LV MCC for CPC Back-up (PP NG Pipeline) | 480V PR MOV STARTER | F | O | R | 2023-02-15 | 2023-03-01 | 2023-02-22 | LV MCC 耗材備件清單 | 設計
20P4300A03-M0021-021 | 20P4300A03-M0021-021 | A2-2-ELM02-V0021A03-021 | Recommended Three (3) Years Spare Parts List for LV MCC for CPC Back-up (PP NG Pipeline) | 480V PR MOV STARTER | F | O | R | 2023-02-15 | 2023-03-01 | 2023-02-22 | 推薦用於 LV MCC 的三 (3) 年備件清單 | 設計
20P4300A03-M0021-022 | 20P4300A03-M0021-022 | A2-2-ELM02-V0021A03-022 | Instructions/Manuals/Procedures for Installation, Operation and Maintenance for LV MCC for CPC Back-up (PP NG Pipeline) | 480V PR MOV STARTER | F | O | R | 2023-02-24 | 2023-03-10 | 2023-03-03 | LV MCC 的安裝、操作和維護說明/手冊/程序 | 設計
20P4300A03-M0021-023 | 20P4300A03-M0021-023 | A2-2-ELM02-V0021A03-023 | Test Certificate/Reports (Type Test) for LV MCC for CPC Back-up (PP NG Pipeline) | 480V PR MOV STARTER | S | O | R | 2023-02-24 | 2023-03-10 | 2023-03-03 | LV MCC 測試證書/報告（型式測試） | 品保
20P4300A03-M0021-024 | 20P4300A03-M0021-024 | A2-2-ELM02-V0021A03-024 | Periodic Preservation Action List for LV MCC for CPC Back-up (PP NG Pipeline) | 480V PR MOV STARTER | F | O | R | 2023-02-15 | 2023-03-01 | 2023-02-22 | LV MCC 定期保存行動表 | 設計
20P4300A03-M0021-025 | 20P4300A03-M0021-025 | A2-2-ELM02-V0021A03-025 | Outline Dimension Drawing (Including Heat Dissipation Data) for LV MCC for CPC Back-up (PP NG Pipeline) | 480V PR MOV STARTER | P | O | R | 2023-02-17 | 2023-03-03 | 2023-02-24 | 低壓 MCC 外形尺寸圖（含散熱數據） | 設計
20P4300A03-M0021-026 | 20P4300A03-M0021-026 | A2-2-ELM02-V0021A03-026 | Material Mill Certificate for LV MCC for CPC Back-up (PP NG Pipeline) | 480V PR MOV STARTER | S | O | R | 2023-02-15 | 2023-03-01 | 2023-02-22 | LV MCC材料工廠證書 | 設計
20P4300A03-M0021-027 | 20P4300A03-M0021-027 | A2-2-ELM02-V0021A03-027 | Training Plan and Material for LV MCC for CPC Back-up (PP NG Pipeline) | 480V PR MOV STARTER | F | O | R | 2023-03-29 | 2023-04-12 | 2023-04-05 | LV MCC 培訓計劃和材料 | 設計
20P4300A03-M0021-028 | 20P4300A03-M0021-028 | A2-2-ELM02-V0021A03-028 | Complete Parts List / Instrument List for LV MCC for CPC Back-up (PP NG Pipeline) | 480V PR MOV STARTER | P | O | R | 2023-02-17 | 2023-03-03 | 2023-02-24 | LV MCC 的完整零件清單/儀器清單 | 設計
20P4300A03-M0021-029 | 20P4300A03-M0021-029 | A2-2-ELM02-V0021A03-029 | Auxiliary Power Requirement for LV MCC for CPC Back-up (PP NG Pipeline) | 480V PR MOV STARTER | P | O | R | 2023-02-17 | 2023-03-03 | 2023-02-24 | 低壓 MCC 的輔助電源要求 | 設計
20P4300A03-M0021-030 | 20P4300A03-M0021-030 | A2-2-ELM02-V0021A03-030 | Insulation and Paint Procedure for LV MCC for CPC Back-up (PP NG Pipeline) | 480V PR MOV STARTER | S | O | R | 2023-02-17 | 2023-03-03 | 2023-02-24 | 低壓 MCC 的絕緣和油漆程序 | 設計
Note on F22: P(3D)： Required vendor documents for 60% 3D Modeling and Model review. P：Primary required vendor documents to support EPC contractor's engineering efforts. S：Secondry required vendor documents to support EPC contractor's engineering efforts. F： Required vendor documents for finish fabrication. M：Manufacture data book.
Note on G22: O：For Client Review (Official) I ：For CTCI Review (Internal)
Note on H22: R：For Review I：For Reference
Note on J22: Vendor Planned Issue Date + 14 calendar days
Note on K22: Vendor Planned Issue Date + 7 calendar days