## VDI
Vendor Document Index
Vendor Document Index should be submitted in quotation stage and finalized in kick-off meeting.
CTCI P.O. No. | 20P4300A03-M0022
P.O. Title | Requisition for Uninterruptible Power Supply (UPS) for CPC Back-up (PP NG Pipeline)
CTCI Requisition No. | 20P4300A03-NF1A.01A
RE Name: | Po-Yen,Chen
1. CTCI Doc. No. |  |  |  |  | 7. Document Status : shall be issued to client for review please key in " O ", for CTCI review only please key in " I "
2. Vendor Document No. |  |  |  |  | 8. Document Issue Type R:For Review, I:For Information
3. Client document No. |  |  |  |  | 9. Vendor plan first issue to CTCI date (yyyy/mm/dd)
4. Description of the document |  |  |  |  | 10. Planned CTCI Approve Date(yyyy/mm/dd)
5. The Main Equipment Tag No. |  |  |  |  | 11. Planned Issue To Client Date (yyyy/mm/dd)
6. Doc Category :
P(3D) : Required vendor documents for 60% 3D Modeling and Model review.
P : Primary required vendor documents to support EPC contractor's engineering efforts.
S : Secondry required vendor documents to support EPC contractor's engineering efforts.
F : Required vendor documents for finish fabrication.
M : Manufacture data / record book.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
CTCI Doc. No. (Required field) | Vendor Doc. No. (Required field) | Client Doc No | Description (Required field) | Main Equipment Tag No. (Required field) | Doc Category (Required field) | Document Status (Required field) | Document Issue Type (Required field) | Vendor Planned 1st Issue Date (Required field) | Planned CTCI Approve Date (Required field) | Planned Issue To Client Date
20P4300A03-M0022-001 | 20P4300A03-M0022-001 | A2-2-ELM02-V0022A03-001 | Vendor Document Index (VDI) for 480V AC UPS for CPC Back-up (PP NG Pipeline) | 480V AC UPS (LNG) | P | I | R | 2023-01-07 | 2023-01-21
20P4300A03-M0022-002 | 20P4300A03-M0022-002 | A2-2-ELM02-V0022A03-002 | Manufacturing Schedule for 480V AC UPS for CPC Back-up (PP NG Pipeline) | 480V AC UPS (LNG) | F | I | R | 2023-01-13 | 2023-01-27
20P4300A03-M0022-003 | 20P4300A03-M0022-003 | A2-2-ELM02-V0022A03-003 | Drawing for 480V AC UPS for CPC Back-up (PP NG Pipeline) | 480V AC UPS (LNG) | P | O | R | 2023-03-31 | 2023-04-14 | 2023-04-21
20P4300A03-M0022-004 | 20P4300A03-M0022-004 | A2-2-ELM02-V0022A03-004 | Battery Monitoring System Drawing for CPC Back-up (PP NG Pipeline) | 480V AC UPS (LNG) | P | O | R | 2023-03-31 | 2023-04-14 | 2023-04-21
20P4300A03-M0022-005 | 20P4300A03-M0022-005 | A2-2-ELM02-V0022A03-005 | Battery Rack Drawing for CPC Back-up (PP NG Pipeline) | 480V AC UPS (LNG) | P | O | R | 2023-03-31 | 2023-04-14 | 2023-04-21
20P4300A03-M0022-006 | 20P4300A03-M0022-006 | A2-2-ELM02-V0022A03-006 | Specification/Catalogs/Datasheet/Calculation Sheets for 480V AC UPS for CPC Back-up (PP NG Pipeline) | 480V AC UPS (LNG) | P | O | R | 2023-03-10 | 2023-03-24 | 2023-03-31
20P4300A03-M0022-007 | 20P4300A03-M0022-007 | A2-2-ELM02-V0022A03-007 | Harmonic Data for 480V AC UPS for CPC Back-up (PP NG Pipeline) | 480V AC UPS (LNG) | P | I | R | 2023-03-31 | 2023-04-14
20P4300A03-M0022-008 | 20P4300A03-M0022-008 | A2-2-ELM02-V0022A03-008 | Routine test report for 480V AC UPS for CPC Back-up (PP NG Pipeline) | 480V AC UPS (LNG) | S | I | R | 2023-09-08 | 2023-09-22
20P4300A03-M0022-009 | 20P4300A03-M0022-009 | A2-2-ELM02-V0022A03-009 | Equipment Quality Plan for 480V AC UPS for CPC Back-up (PP NG Pipeline) | 480V AC UPS (LNG) | P | O | R | 2023-03-17 | 2023-03-31 | 2023-04-07
20P4300A03-M0022-010 | 20P4300A03-M0022-010 | A2-2-ELM02-V0022A03-010 | Certificate of Conformity for 480V AC UPS for CPC Back-up (PP NG Pipeline) | 480V AC UPS (LNG) | S | I | R | 2023-10-27 | 2023-11-10
20P4300A03-M0022-011 | 20P4300A03-M0022-011 | A2-2-ELM02-V0022A03-011 | Test Report for 480V AC UPS for CPC Back-up (PP NG Pipeline) | 480V AC UPS (LNG) | S | O | R | 2023-09-28 | 2023-10-12 | 2023-10-19
20P4300A03-M0022-012 | 20P4300A03-M0022-012 | A2-2-ELM02-V0022A03-012 | Monthly Status Reports for 480V AC UPS for CPC Back-up (PP NG Pipeline) | 480V AC UPS (LNG) | F | I | R | 2023-01-17 | 2023-01-31
20P4300A03-M0022-013 | 20P4300A03-M0022-013 | A2-2-ELM02-V0022A03-013 | Packing List for 480V AC UPS for CPC Back-up (PP NG Pipeline) | 480V AC UPS (LNG) | F | I | R | 2023-10-14 | 2023-10-28
20P4300A03-M0022-014 | 20P4300A03-M0022-014 | A2-2-ELM02-V0022A03-014 | Sub-Vendor List for 480V AC UPS for CPC Back-up (PP NG Pipeline) | 480V AC UPS (LNG) | S | I | R | 2023-05-26 | 2023-06-09
20P4300A03-M0022-015 | 20P4300A03-M0022-015 | A2-2-ELM02-V0022A03-015 | Manufacturer's Data/Record Book (MDRB) Index for 480V AC UPS for CPC Back-up (PP NG Pipeline) | 480V AC UPS (LNG) | M | I | R | 2023-10-20 | 2023-11-03
20P4300A03-M0022-016 | 20P4300A03-M0022-016 | A2-2-ELM02-V0022A03-016 | Manufacturer's Data/Record Book (MDRB) for 480V AC UPS for CPC Back-up (PP NG Pipeline) | 480V AC UPS (LNG) | M | I | R | 2023-10-27 | 2023-11-10
20P4300A03-M0022-017 | 20P4300A03-M0022-017 | A2-2-ELM02-V0022A03-017 | Mandatory Spare Parts List for 480V AC UPS for CPC Back-up (PP NG Pipeline) | 480V AC UPS (LNG) | F | I | R | 2023-07-14 | 2023-07-28
20P4300A03-M0022-018 | 20P4300A03-M0022-018 | A2-2-ELM02-V0022A03-018 | Recommended Three (3) Years Spare Parts List for 480V AC UPS for CPC Back-up (PP NG Pipeline) | 480V AC UPS (LNG) | F | I | R | 2023-07-14 | 2023-07-28
20P4300A03-M0022-019 | 20P4300A03-M0022-019 | A2-2-ELM02-V0022A03-019 | Special Tool List for 480V AC UPS for CPC Back-up (PP NG Pipeline) | 480V AC UPS (LNG) | F | I | R | 2023-07-14 | 2023-07-28
20P4300A03-M0022-020 | 20P4300A03-M0022-020 | A2-2-ELM02-V0022A03-020 | Instructions/Manuals/Procedures for Installation, Operation and Maintenance for 480V AC UPS for CPC Back-up (PP NG Pipeline) | 480V AC UPS (LNG) | F | O | R | 2023-10-06 | 2023-10-20 | 2023-10-27
20P4300A03-M0022-021 | 20P4300A03-M0022-021 | A2-2-ELM02-V0022A03-021 | Test Certificate/Reports (Type Test) for 480V AC UPS for CPC Back-up (PP NG Pipeline) | 480V AC UPS (LNG) | S | O | R | 2023-03-31 | 2023-04-14 | 2023-04-21
20P4300A03-M0022-022 | 20P4300A03-M0022-022 | A2-2-ELM02-V0022A03-022 | Periodic Preservation Action List for 480V AC UPS for CPC Back-up (PP NG Pipeline) | 480V AC UPS (LNG) | F | I | R | 2023-06-16 | 2023-06-30
20P4300A03-M0022-023 | 20P4300A03-M0022-023 | A2-2-ELM02-V0022A03-023 | Material Mill Certificate for 480V AC UPS for CPC Back-up (PP NG Pipeline) | 480V AC UPS (LNG) | S | I | R | 2023-09-08 | 2023-09-22
20P4300A03-M0022-024 | 20P4300A03-M0022-024 | A2-2-ELM02-V0022A03-024 | Training Plan and Material for 480V AC UPS for CPC Back-up (PP NG Pipeline) | 480V AC UPS (LNG) | F | I | R | 2023-10-14 | 2023-10-28
20P4300A03-M0022-025 | 20P4300A03-M0022-025 | A2-2-ELM02-V0022A03-025 | Complete Parts List / Instrument List for 480V AC UPS for CPC Back-up (PP NG Pipeline) | 480V AC UPS (LNG) | P | I | R | 2023-05-26 | 2023-06-09
20P4300A03-M0022-026 | 20P4300A03-M0022-026 | A2-2-ELM02-V0022A03-026 | Painting Schedule for 480V AC UPS for CPC Back-up (PP NG Pipeline) | 480V AC UPS (LNG) | S | I | R | 2023-05-26 | 2023-06-09
20P4300A03-M0022-027 | 20P4300A03-M0022-027 | A2-2-ELM02-V0022A03-027 | Packing, Delivery, Storage and Unpacking Procedure for CPC Back-up (PP NG Pipeline) | 480V AC UPS (LNG) | F | I | R | 2023-10-06 | 2023-10-20
Note on F22: P(3D)： Required vendor documents for 60% 3D Modeling and Model review. P：Primary required vendor documents to support EPC contractor's engineering efforts. S：Secondry required vendor documents to support EPC contractor's engineering efforts. F： Required vendor documents for finish fabrication. M：Manufacture data book.
Note on G22: O：For Client Review (Official) I ：For CTCI Review (Internal)
Note on H22: R：For Review I：For Reference
Note on J22: Vendor Planned Issue Date + 14 calendar days
Note on K22: Vendor Planned Issue Date + 7 calendar days
Note on D25: rex: 包含如下文件 1.General Arrangement Drawing 2.Alarm/Trip/Signal Mapping List 3.Cable List/Schedule 4.Single Line Diagram 5.Schematic and Connection Diagram 6.Outline Dimension Drawing (Including Heat Dissipation Data) 7.Auxiliary Power Requirement
Note on D28: rex: 包含如下文件 1.Specification and Catalogs 2.Data Sheet 3.Calculation Sheets
Note on D30: rex: 此文件同自主出廠試驗報告，包含 刪除自主中間檢查報告
Note on D31: rex: 包含如下文件 1.Test and Inspection Procedure (Including Factory Acceptance Test ) 2.Inspection Test Plan (ITP) Site Acceptance Test將與分項施工品質計畫合併，由中鼎工地電機組或品管組提送給業主。
Note on D33: rex: 此文件同Factory Acceptance Test (FAT) Report/Record Sheet 刪除Site Acceptance Test Report/Record Sheet，此報告由中鼎工地提送給業主。
Note on D48: rex: 此文件同Insulation and Paint Procedure
Note on D49: rex: 此文件同Packing, Knockdown and Transportation Procedure