## VDI
Vendor Document Index
Vendor Document Index should be submitted in quotation stage and finalized in kick-off meeting.
CTCI P.O. No. | 20P4300A04-M0023
P.O. Title | Requisition for Uninterruptible Power Supply (UPS) and Distribution Panel for CPC Back-up (New)
CTCI Requisition No. | 20P4300A04-NF1A.01B
RE Name: | Po-Yen,Chen
1. CTCI Doc. No. |  |  |  |  | 7. Document Status : shall be issued to client for review please key in " O ", for CTCI review only please key in " I "
2. Vendor Document No. |  |  |  |  | 8. Document Issue Type R:For Review, I:For Information
3. Client document No. |  |  |  |  | 9. Vendor plan first issue to CTCI date (yyyy/mm/dd)
4. Description of the document |  |  |  |  | 10. Planned CTCI Approve Date(yyyy/mm/dd)
5. The Main Equipment Tag No. |  |  |  |  | 11. Planned Issue To Client Date (yyyy/mm/dd)
6. Doc Category :
P(3D) : Required vendor documents for 60% 3D Modeling and Model review.
P : Primary required vendor documents to support EPC contractor's engineering efforts.
S : Secondry required vendor documents to support EPC contractor's engineering efforts.
F : Required vendor documents for finish fabrication.
M : Manufacture data / record book.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
CTCI Doc. No. (Required field) | Vendor Doc. No. (Required field) | Client Doc No | Description (Required field) | Main Equipment Tag No. (Required field) | Doc Category (Required field) | Document Status (Required field) | Document Issue Type (Required field) | Vendor Planned 1st Issue Date (Required field) | Planned CTCI Approve Date (Required field) | Planned Issue To Client Date
20P4300A04-M0023-001 | 20P4300A04-M0023-001 | A2-2-ELM02-V0023A04-001 | Vendor Document Index (VDI) for 120V AC UPS for CPC Back-up (New) | UPS2 | P | I | R | 2023-01-07 | 2023-01-21
20P4300A04-M0023-002 | 20P4300A04-M0023-002 | A2-2-ELM02-V0023A04-002 | Manufacturing Schedule for 120V AC UPS for CPC Back-up (New) | UPS2 | F | I | R | 2023-01-13 | 2023-01-27
20P4300A04-M0023-003 | 20P4300A04-M0023-003 | A2-2-ELM02-V0023A04-003 | Drawing for 120V AC UPS for CPC Back-up (New) | UPS2 | P | O | R | 2023-03-31 | 2023-04-14 | 2023-04-21
20P4300A04-M0023-004 | 20P4300A04-M0023-004 | A2-2-ELM02-V0023A04-004 | Specification/Catalogs/Datasheet/Calculation Sheets for 120V AC UPS for CPC Back-up (New) | UPS2 | P | O | R | 2023-03-10 | 2023-03-24 | 2023-03-31
20P4300A04-M0023-005 | 20P4300A04-M0023-005 | A2-2-ELM02-V0023A04-005 | Routine test report for 120V AC UPS for CPC Back-up (New) | UPS2 | S | I | R | 2023-09-08 | 2023-09-22
20P4300A04-M0023-006 | 20P4300A04-M0023-006 | A2-2-ELM02-V0023A04-006 | Equipment Quality Plan for 120V AC UPS for CPC Back-up (New) | UPS2 | P | O | R | 2023-03-17 | 2023-03-31 | 2023-04-07
20P4300A04-M0023-007 | 20P4300A04-M0023-007 | A2-2-ELM02-V0023A04-007 | Certificate of Conformity for 120V AC UPS for CPC Back-up (New) | UPS2 | S | I | I | 2023-10-27 | 2023-11-10
20P4300A04-M0023-008 | 20P4300A04-M0023-008 | A2-2-ELM02-V0023A04-008 | Test Report for 120V AC UPS for CPC Back-up (New) | UPS2 | S | O | R | 2023-09-28 | 2023-10-12 | 2023-10-19
20P4300A04-M0023-009 | 20P4300A04-M0023-009 | A2-2-ELM02-V0023A04-009 | Monthly Status Report for 120V AC UPS for CPC Back-up (New) | UPS2 | F | I | I | 2023-01-17 | 2023-01-31
20P4300A04-M0023-010 | 20P4300A04-M0023-010 | A2-2-ELM02-V0023A04-010 | Packing List for 120V AC UPS for CPC Back-up (New) | UPS2 | F | I | I | 2023-10-14 | 2023-10-28
20P4300A04-M0023-011 | 20P4300A04-M0023-011 | A2-2-ELM02-V0023A04-011 | Sub-Vendor List for 120V AC UPS for CPC Back-up (New) | UPS2 | S | I | R | 2023-05-26 | 2023-06-09
20P4300A04-M0023-012 | 20P4300A04-M0023-012 | A2-2-ELM02-V0023A04-012 | Manufacturer's Data/Record Book (MDRB) Index for 120V AC UPS for CPC Back-up (New) | UPS2 | M | I | R | 2023-10-20 | 2023-11-03
20P4300A04-M0023-013 | 20P4300A04-M0023-013 | A2-2-ELM02-V0023A04-013 | Manufacturer's Data/Record Book (MDRB) for 120V AC UPS for CPC Back-up (New) | UPS2 | M | I | R | 2023-10-27 | 2023-11-10
20P4300A04-M0023-014 | 20P4300A04-M0023-014 | A2-2-ELM02-V0023A04-014 | Instructions/Manuals/Procedures for Installation, Operation and Maintenance for 120V AC UPS for CPC Back-up (New) | UPS2 | F | O | R | 2023-10-06 | 2023-10-20 | 2023-10-27
20P4300A04-M0023-015 | 20P4300A04-M0023-015 | A2-2-ELM02-V0023A04-015 | Periodic Preservation Action List for 120V AC UPS for CPC Back-up (New) | UPS2 | F | I | R | 2023-06-16 | 2023-06-30
20P4300A04-M0023-016 | 20P4300A04-M0023-016 | A2-2-ELM02-V0023A04-016 | Material Mill Certificate for 120V AC UPS for CPC Back-up (New) | UPS2 | F | I | I | 2023-09-08 | 2023-09-22
20P4300A04-M0023-017 | 20P4300A04-M0023-017 | A2-2-ELM02-V0023A04-017 | Training Plan and Material for 120V AC UPS for CPC Back-up (New) | UPS2 | F | I | R | 2023-10-14 | 2023-10-28
20P4300A04-M0023-018 | 20P4300A04-M0023-018 | A2-2-ELM02-V0023A04-018 | Painting Schedule for 120V AC UPS for 120V AC UPS for CPC Back-up (New) | UPS2 | F | I | I | 2023-05-26 | 2023-06-09
Note on F22: P(3D)： Required vendor documents for 60% 3D Modeling and Model review. P：Primary required vendor documents to support EPC contractor's engineering efforts. S：Secondry required vendor documents to support EPC contractor's engineering efforts. F： Required vendor documents for finish fabrication. M：Manufacture data book.
Note on G22: O：For Client Review (Official) I ：For CTCI Review (Internal)
Note on H22: R：For Review I：For Reference
Note on J22: Vendor Planned Issue Date + 14 calendar days
Note on K22: Vendor Planned Issue Date + 7 calendar days
Note on D25: rexhu: 此文件包含以下文件: 1.General Arrangement Drawing (Including Foundation Design Base and Anchor Details) 2.Single Line Diagram 3.Schematic and Connection Diagram 4.Outline Dimension Drawing (Including Heat Dissipation Data) 5.Auxiliary Power Requirement
Note on D26: rexhu: 此文件包含以下文件: 1.Specification/Catalogs/Datasheet 2.Calculation Sheets
Note on D27: rexhu: 此文件等同自主出廠試驗報告 台達RT型號UPS為標準品，無自主中間檢查報告、Test Certificate/Reports (Type Test)及Packing, Knockdown and Transportation可提供，故刪除之。
Note on D28: rexhu: 此文件包含以下文件: 1.Test and Inspection Procedure (Including Factory Acceptance Test) 2.Inspection Test Plan (ITP) Site Acceptance Test將與分項施工品質計畫合併，由中鼎工地電機組或品管組提送給業主。
Note on D30: rexhu: 此文件同Factory Acceptance Test (FAT) Report/Record Sheet 刪除Site Acceptance Test Report/Record Sheet，此報告由中鼎工地提送給業主。
Note on D40: rexhu: 此文件同Insulation and Paint Procedure