## VDI-QOC-6001
Vendor Document Index
Vendor Document Index should be submitted in quotation stage and finalized in kick-off meeting.
CTCI P.O. No. | 20P4300A03-M0023
P.O. Title | Requisition for Pipeline Closure (AG) of CPC Back-up (PPNG Pipeline)
CTCI Requisition No. | 20P4300A03-M99A.51A
RE Name: | Rod Wu
1. CTCI Doc. No. | [5 empty] | 7. Document Status : shall be issued to client for review please key in " O ", for CTCI review only please key in " I "
2. Vendor Document No. | [5 empty] | 8. Document Issue Type R:For Review, I:For Information
3. Client document No. | [5 empty] | 9. Vendor plan first issue to CTCI date (yyyy/mm/dd)
4. Description of the document | [5 empty] | 10. Planned CTCI Approve Date(yyyy/mm/dd)
5. The Main Equipment Tag No. | [5 empty] | 11. Planned Issue To Client Date (yyyy/mm/dd)
6. Doc Category :
P(3D) : Required vendor documents for 60% 3D Modeling and Model review.
P : Primary required vendor documents to support EPC contractor's engineering efforts.
S : Secondry required vendor documents to support EPC contractor's engineering efforts.
F : Required vendor documents for finish fabrication.
M : Manufacture data / record book.
CTCI Doc. No. | Vendor Doc. No. | Client Doc No | Description |  | Main Equipment Tag No. | Doc Category | Document Status | Document Issue Type | Vendor Planned 1st Issue Date | Planned CTCI Approve Date | Planned Issue To Client Date | NOTE
20P4300A03-M0023-001 | 20P4300A03-M0023-TCTI-001 | A2-2-PEM02-V0023A03-001 | Vendor Document Index |  | QOC-6001 | S | I | R | 02/17/2023
20P4300A03-M0023-002 | 20P4300A03-M0023-TCTI-002 | A2-2-PEM02-V0023A03-002 | Fabrication/Production Schedule Plan (Include Design, Materials Purchasing, Fabrication, Testing and Inspections and Packing...) |  | QOC-6001 | S | I | R | 2W after receipt of code 1 Approved drawing.
20P4300A03-M0023-003 | 20P4300A03-M0023-TCTI-003 | A2-2-PEM02-V0023A03-003 | Tables Of Contents For MDB |  | QOC-6001 | M | I | R | 02/24/2023
20P4300A03-M0023-004 | 20P4300A03-M0023-TCTI-004 | A2-2-PEM02-V0023A03-004 | Organization Chart |  | QOC-6001 | S | I | I | 03/06/2023
20P4300A03-M0023-005 | 20P4300A03-M0023-TCTI-005 | A2-2-PEM02-V0023A03-005 | Maunfacturer Registration Certificate |  | QOC-6001 | M | I | I | 02/22/2023
20P4300A03-M0023-006 | 20P4300A03-M0023-TCTI-006 | A2-2-PEM02-V0023A03-006 | TDW India Company Registration Certificate |  | QOC-6001 | M | I | I | 02/02/2023
20P4300A03-M0023-006 | 20P4300A03-M0023-TCTI-006 | A2-2-PEM02-V0023A03-006 | GA Drawing along with Design Calculation |  | QOC-6001 | 2D | I | R | 02/22/2023 |  |  | Drawings in 2D PDF version shall be provided
20P4300A03-M0023-007 | 20P4300A03-M0023-TCTI-007 | A2-2-PEM02-V0023A03-007 | GA Drawing along with Design Calculation for Pig-SIG |  | QOC-6001 | 2D | I | R | 02/24/2023 |  |  | Drawings in 2D PDF version shall be provided
20P4300A03-M0023-008 | 20P4300A03-M0023-TCTI-008 | A2-2-PEM02-V0023A03-008 | Nameplate Drawings (Including Method of Identification of Spool Piece) |  | QOC-6001 | S | I | R | 02/22/2023
20P4300A03-M0023-009 | 20P4300A03-M0023-TCTI-009 | A2-2-PEM02-V0023A03-009 | Inspection Test Plan for Closure |  | QOC-6001 | P | I | I | 02/22/2023
20P4300A03-M0023-010 | 20P4300A03-M0023-TCTI-010 | A2-2-PEM02-V0023A03-010 | Inspection Test Plan for Pig SIG |  | QOC-6001 | P | I | I | 02/22/2023
20P4300A03-M0023-011 | 20P4300A03-M0023-TCTI-011 | A2-2-PEM02-V0023A03-011 | Vendor Catalogues |  | QOC-6001 | F | I | I | 02/22/2023
20P4300A03-M0023-012 | 20P4300A03-M0023-TCTI-012 | A2-2-PEM02-V0023A03-012 | ISO/ CE Certificate (ISO 9001/ API Spec Q1) & HSE Assurance (ISO 14001 or EQ.) |  | QOC-6001 | S | I | I | 02/22/2023
20P4300A03-M0023-013 | 20P4300A03-M0023-TCTI-013 | A2-2-PEM02-V0023A03-013 | Experience List |  | QOC-6001 | NA | I | I | 02/22/2023
20P4300A03-M0023-014 | 20P4300A03-M0023-TCTI-014 | A2-2-PEM02-V0023A03-014 | Manual Of Installation Operating & Maintenance (IOM) |  | QOC-6001 | F | I | I | 02/22/2023
20P4300A03-M0023-015 | 20P4300A03-M0023-TCTI-015 | A2-2-PEM02-V0023A03-015 | Hydrostatic or Pneumatic Test Procedures |  | QOC-6001 | M | I | R | 02/22/2023
20P4300A03-M0023-016 | 20P4300A03-M0023-TCTI-016 | A2-2-PEM02-V0023A03-016 | Non-Destructive Test Procedures |  | QOC-6001 | S | I | R | 02/22/2023
20P4300A03-M0023-017 | 20P4300A03-M0023-TCTI-017 | A2-2-PEM02-V0023A03-017 | Weld Procedure Specifications & PQR |  | QOC-6001 | S | I | I | 02/22/2023
20P4300A03-M0023-018 | 20P4300A03-M0023-TCTI-018 | A2-2-PEM02-V0023A03-018 | Packing Procedures for Shipping |  | QOC-6001 | S | I | I | 02/22/2023
20P4300A03-M0023-019 | 20P4300A03-M0023-TCTI-019 | A2-2-PEM02-V0023A03-019 | Quality Dossier Report (With Index) | PMI Report for PIG-SIG® V | QOC-6001 | S | I | R | 2 Weeks after Inspection of the PIG-SIG® V
|  |  |  | Inspection And Test Reports (All Other Test Reports if applicable) | QOC-6001 | F | I | I | 18 Week from drawing Approval
|  |  |  | Quality documents with MTR (Material Test Report ) | QOC-6001 | F | I | I | 18 Week from drawing Approval
|  |  |  | Painting Inspection Report | QOC-6001 | F | I | R | 18 Week from drawing Approval
|  |  |  | Hydrotest Report for Closure | QOC-6001 | F | I | R | 18 Week from drawing Approval
|  |  |  | Hydrotest Report for Pig-SIG | QOC-6001 | F | I | R | 18 Week from drawing Approval
|  |  |  | Non-Destructive Test Reports | QOC-6001 | F | I | R | 18 Week from drawing Approval |  |  | Report for Dye penetration inspection on the welding shall be provided and it will be a part of Qualiy dossier only
|  |  |  | Origin Certificate | QOC-6001 | M | I | I | after 18 weeks from approved drawing |  |  | Certificate of Origin signed and stamped by federation of Gujarat Industries shall be provided
|  |  |  | EN 10204-3.2 Testing Report (Done in TUV Scope for Raw Materials-Closure) | QOC-6001 | F | I | R | 18 Week from drawing Approval |  |  | 3.2 Certification shall be mentioned on the MTC of raw forgings of Closures dully signed by TUV
|  |  |  | EN 10204-3.2 Testing Report (Done in TUV Scope for Raw Materials-Pig SIG) | QOC-6001 | F | I | R | 18 Week from drawing Approval |  |  | 3.2 Certification shall be mentioned on the MTC of Flange of PIG-SIG®V Flange dully signed by TUV
|  |  |  | Calibration Certificate | QOC-6001 | F | I | I | 18 Week from drawing Approval
20P4300A03-M0023-020 | 20P4300A03-M0023-TCTI-020 | A2-2-PEM02-V0023A03-020 | Material Test Certificate (MTC) and COC (EN 10204-3.2 Testing with TUV Certificate for Closure and Pig-SIG) |  | QOC-6001 | F | I | I | 18 Week from drawing Approval
20P4300A03-M0023-021 | 20P4300A03-M0023-TCTI-021 | A2-2-PEM02-V0023A03-021 | Origin Certificate |  | QOC-6001 | M | I | I | after 18 weeks from approved drawing |  |  | Certificate of Origin signed and stamped by federation of Gujarat Industries shall be provided
20P4300A03-M0023-022 | 20P4300A03-M0023-TCTI-022 | A2-2-PEM02-V0023A03-022 | Packing List (Including Inspection Release Certificate) (a) Wooden Case Package or Fumigation Certificate, or (b) Non-Wooden Case Packing Certificate, or (c) Non-Conifer Wooden Case Certificate |  | QOC-6001 | M | I | R | after 18 weeks from approved drawing
20P4300A03-M0023-023 | 20P4300A03-M0023-TCTI-023 | A2-2-PEM02-V0023A03-023 | Manufacturer’s Data/Record Book |  | QOC-6001 | M | I | I | 21 week after drawing approval
20P4300A03-M0023-024 | 20P4300A03-M0023-TCTI-024 | A2-2-PEM02-V0023A03-024 | Packing Photograph and Packing List with Dimensional details and weights |  | QOC-6001 | M | I | I | 1 week after receipt of dispatch clearance from customer |  |  | Packing list along with packing photograph shall be provided
20P4300A03-M0023-025 | 20P4300A03-M0023-TCTI-025 | A2-2-PEM02-V0023A03-025 | User's Design Requirements (UDR) |  | QOC-6001 | F | I | R | 02/22/2023
20P4300A03-M0023-026 | 20P4300A03-M0023-TCTI-026 | A2-2-PEM02-V0023A03-026 | Paint procedure |  | QOC-6001 | M | I | I | 02/22/2023
20P4300A03-M0023-027 | 20P4300A03-M0023-TCTI-027 | A2-2-PEM02-V0023A03-027 | Spare Parts For Normal Operation (2 Years) |  | QOC-6001 | M | I | I
TCTI Comments:
1. Maunfacturer Registration Certificate is same as TDW India Company Registration Certificate, therefore remove TDW India Company Registration Certificate.
2. 2D PDF for GA Drawing along with Design Calculation should be provided.
3. Quality Plan is part of ITP, therefore not add the Quality Plan
4. All the Inspection and Test reports are all parts of Quality Dossier Report, revised the document name.
5. EN 10204-3.2 Testing with TUV Certificate for Closure and Pig-SIG will be merged into MTC
6. Origin Certificate is an individual document. Added separate report.
7. "Manufacturing Data Book Index" is same as "Tables Of Contents For MDB".
8. Packing Photograph and Packing List with detail Dimensions and Weight shoulde be provided, not Packing Drawing.
9. Document Nos. have been revised.
10. The Customer Doc. Nos. added.
11. CTCI PO No. and PO Title have been revised.
Note on G22: P(3D)： Required vendor documents for 60% 3D Modeling and Model review. P：Primary required vendor documents to support EPC contractor's engineering efforts. S：Secondry required vendor documents to support EPC contractor's engineering efforts. F： Required vendor documents for finish fabrication. M：Manufacture data book.
Note on H22: O：For Client Review (Official) I ：For CTCI Review (Internal)
Note on I22: R：For Review I：For Reference
Note on K22: Vendor Planned Issue Date + 14 calendar days
Note on L22: Vendor Planned Issue Date + 7 calendar days