## Sheet1
[5 empty] | Date: | 2023-02-02
[5 empty] | Ref. Transmittal No.: | D-D1-GEA-GEL-23-0052
DATAN COMBINED CYCLE POWER PLANT EXPANSION PROJECT DRAWING / DOCUMENT SUBMITTAL LIST
CLASS - A: Approval R: Review I: Information F: Final AB: As-built Z: Other
NO. | CUSTOMER DRAWING NO. | REV. | DOCUMENT TITLE | CLASS | CONTRACTOR DOCUMENT NO. | REMARK
1 | D9-1-AOC01-D1001 | 1 | Unit 9 Gas Turbine and Electrical Building Basement Floor Plan | FC | DTA/90/W/UMB---CEP2/CF/001
2 | D9-1-AOC01-D1002 | 1 | Unit 9 Gas Turbine and Electrical Building Ground Floor Plan | FC | DTA/90/W/UMB---CEP2/CF/002
3 | D9-1-AOC01-D1003 | 1 | Unit 9 Gas Turbine and Electrical Building Second Floor Plan | FC | DTA/90/W/UMB---CEP2/CF/003
4 | D9-1-AOC01-D1004 | 1 | Unit 9 Gas Turbine and Electrical Building Third Floor Plan | FC | DTA/90/W/UMB---CEP2/CF/004
5 | D9-1-AOC01-D1005 | 1 | Unit 9 Gas Turbine and Electrical Building Fourth And Roof Floor Plan | FC | DTA/90/W/UMB---CEP2/CF/005
6 | D9-1-AOC01-D1006 | 1 | Unit 9 Gas Turbine and Electrical Building Low Roof Floor Plan | FC | DTA/90/W/UMB---CEP2/CF/006
7 | D9-1-AOC01-D1007 | 1 | Unit 9 Gas Turbine and Electrical Building High Roof Floor Plan | FC | DTA/90/W/UMB---CEP2/CF/007
8 | D9-1-AOC01-D1008 | 1 | Unit 9 Gas Turbine and Electrical Building East Elevation | FC | DTA/90/W/UMB---CEP2/CF/008
9 | D9-1-AOC01-D1009 | 1 | Unit 9 Gas Turbine and Electrical Building West Elevation | FC | DTA/90/W/UMB---CEP2/CF/009
10 | D9-1-AOC01-D1010 | 1 | Unit 9 Gas Turbine and Electrical Building South Elevation | FC | DTA/90/W/UMB---CEP2/CF/010
11 | D9-1-AOC01-D1011 | 1 | Unit 9 Gas Turbine and Electrical Building North Elevation | FC | DTA/90/W/UMB---CEP2/CF/011
12 | D9-1-AOC01-D1012 | 1 | Unit 9 Gas Turbine and Electrical Building Section A-A | FC | DTA/90/W/UMB---CEP2/CF/012
13 | D9-1-AOC01-D1014 | 1 | Unit 9 Gas Turbine and Electrical Building Section C-C | FC | DTA/90/W/UMB---CEP2/CF/014
14 | D9-1-AOC01-D1015 | 1 | Unit 9 Gas Turbine and Electrical Building Wall Section (1/5) | FC | DTA/90/W/UMB---CEP2/CF/015
15 | D9-1-AOC01-D1016 | 1 | Unit 9 Gas Turbine and Electrical Building Wall Section (2/5) | FC | DTA/90/W/UMB---CEP2/CF/016
16 | D9-1-AOC01-D1017 | 1 | Unit 9 Gas Turbine and Electrical Building Wall Section (3/5) | FC | DTA/90/W/UMB---CEP2/CF/017
17 | D9-1-AOC01-D1018 | 1 | Unit 9 Gas Turbine and Electrical Building Wall Section (4/5) | FC | DTA/90/W/UMB---CEP2/CF/018
18 | D9-1-AOC01-D1019 | 1 | Unit 9 Gas Turbine and Electrical Building Wall Section (5/5) | FC | DTA/90/W/UMB---CEP2/CF/019
19 | D9-1-AOC01-D1034 | 1 | Unit 9 Gas Turbine and Electrical Building Door & Window Schedule (1/4) | FC | DTA/90/W/UMB---CEP2/CF/034
20 | D9-1-AOC01-D1035 | 1 | Unit 9 Gas Turbine and Electrical Building Door & Window Schedule (2/4) | FC | DTA/90/W/UMB---CEP2/CF/035
21 | D9-1-AOC01-D1036 | 1 | Unit 9 Gas Turbine and Electrical Building Door & Window Schedule (3/4) | FC | DTA/90/W/UMB---CEP2/CF/036
22 | D9-1-AOC01-D1038 | 1 | Unit 9 Gas Turbine and Electrical Building Ground Floor Fire Zone Division Plan | FC | DTA/90/W/UMB---CEP2/CF/038
23 | D9-1-AOC01-D1039 | 1 | Unit 9 Gas Turbine and Electrical Building Second Floor Fire Zone Division Plan | FC | DTA/90/W/UMB---CEP2/CF/039
24 | D9-1-AOC01-D1046 | 1 | Unit 9 Gas Turbine and Electrical Building Exterior Wall Panel Details | FC | DTA/90/W/UMB---CEP2/CF/046
25 | D9-1-AOC01-D1047 | 1 | Unit 9 Gas Turbine and Electrical Building Door & Window Schedule (4/4) | FC | DTA/90/W/UMB---CEP2/CF/047